ROSES OS

Communication Architecture

Cost Summary

_______________________________________________

Prepared by: Jennifer Brooke Lawless

Date: March 8, 2026

Version: 1.0 -- For Team Review

Source: Communication Architecture for the Age of AI (V2, 2025-2026)

# Overview

This document provides a cost summary for implementing the strategic initiatives outlined in the Communication Architecture for the Age of AI PDF. This is a standalone estimate covering the GEO (Generative Engine Optimization) strategy, platform ecosystem buildout, partnership engagement, and supporting infrastructure described in that 21-page strategic framework.

This cost summary is separate from and complementary to the Scope of Work & Economic Proposal (which covers platform development, brand book, manuals, and design system). Some items overlap -- those are noted where applicable.

_______________________________________________

# 1. Pre-Launch Strategy Initiatives (5-8 Month Window)

The Communication Architecture identifies a critical 5-8 month pre-launch window before the book publication. The following workstreams are required to prepare the knowledge ecosystem.

## 1.1 Substack Migration & Publication Setup

Migrate 29-issue newsletter archive to Substack. Establish as named, branded publication. Configure paid subscription tier. Set up recommendation network integrations.

Deliverables: Branded Substack publication live with full archive, paid tier configured, discovery settings optimized.

|  | Market Value | Contribution Rate (10%) |
| --- | --- | --- |
| Total | $4,500 | $450 |

## 1.2 Long-Form Blog Essays -- GEO Core Content

Write and publish 8-12 definitional long-form essays on key Roses OS concepts (Coherence, Remembrance, The Rose Practice, Inner Technology, The Field, Loving Presence). Structured with proper headers, schema-ready, bilingual (EN + ES). Each 2,000-4,000 words, structured to directly answer AI-asked questions.

|  | Market Value | Contribution Rate (10%) |
| --- | --- | --- |
| Total | $18,000 | $1,800 |

## 1.3 Schema Markup & Technical Infrastructure

Implement schema.org markup across the Roses OS website (Organization, Person, Course, Article, FAQPage, DefinedTerm). Optimize page titles, meta descriptions, clean URLs, alt text, sitemap. Add transcripts infrastructure for audio/video content.

|  | Market Value | Contribution Rate (10%) |
| --- | --- | --- |
| Total | $12,000 | $1,200 |

Note: This overlaps with the "GEO / Content Architecture" project in the Scope of Work ($12,000 market). If engaged through that milestone, this line item would be consolidated.

## 1.4 YouTube Channel -- Spanish Language

Launch dedicated Spanish-language YouTube channel. Establish conceptually structured content framework (titles, descriptions, chapter markers, transcripts aligned to Roses OS vocabulary). Initial 8-12 videos produced and optimized.

|  | Market Value | Contribution Rate (10%) |
| --- | --- | --- |
| Total | $22,000 | $2,200 |

## 1.5 YouTube Channel -- English Language

Launch English-language YouTube channel with same conceptual structure. Initial 6-8 videos produced and optimized.

|  | Market Value | Contribution Rate (10%) |
| --- | --- | --- |
| Total | $16,000 | $1,600 |

## 1.6 Citation Network -- Strategic Podcast Appearances

Research, outreach, booking, and preparation for 2-3 strategic podcast appearances on credible shows in consciousness, leadership, and inner development. Priority on Spanish-language podcasts. Includes pre-appearance coaching, talking point development, and post-appearance content repurposing.

|  | Market Value | Contribution Rate (10%) |
| --- | --- | --- |
| Total | $9,000 | $900 |

## 1.7 Community Voice Program

Design and launch structured program for collecting practitioner essays, written testimonials, public reflections using Roses OS language. Create submission framework, editorial guidelines, and publishing workflow.

|  | Market Value | Contribution Rate (10%) |
| --- | --- | --- |
| Total | $6,000 | $600 |

## 1.8 Wikipedia Groundwork

Research Wikipedia notability requirements. Map citation gaps. Develop sourcing strategy. Prepare draft entries for the school, founder, and key concepts. Accumulate qualifying independent citations.

|  | Market Value | Contribution Rate (10%) |
| --- | --- | --- |
| Total | $5,000 | $500 |

_______________________________________________

# 2. Conversion Bridge Design

The Communication Architecture describes a 5-step conversion journey from AI recommendation to enrolled student:

1. AI recommendation -- the person discovers Roses OS through a response to a question they asked

2. Structured arrival -- they land on a page that clearly explains the framework

3. Depth confirmation -- they read an essay, watch a talk, or explore the newsletter

4. Community signal -- they encounter voices of students and practitioners

5. Clear invitation -- a specific, well-designed pathway to the next step

Scope: Design and build the full conversion bridge across the Roses OS website. Responsive, bilingual (EN + ES).

|  | Market Value | Contribution Rate (10%) |
| --- | --- | --- |
| Total | $14,000 | $1,400 |

_______________________________________________

# 3. Strategic Partnerships

The Communication Architecture identifies three partnership profiles essential to accelerating the ecosystem. These represent engagement costs, not ongoing retainers.

## 3.1 Digital Infrastructure Partner

Engage a systematic content distribution partner to build repeatable "build once, distribute forever" content operations. Establish workflows for turning founder ideas into structured multi-platform content.

|  | Market Value | Contribution Rate (10%) |
| --- | --- | --- |
| Total | $15,000 | $1,500 |

## 3.2 YouTube Strategy Partner

Engage a YouTube thought-leader strategist for channel strategy, algorithmic optimization, and content structure consulting for both EN + ES channels.

|  | Market Value | Contribution Rate (10%) |
| --- | --- | --- |
| Total | $10,000 | $1,000 |

## 3.3 Hispanic Podcast Ecosystem Partner

Identify, outreach, and establish relationship with 1-2 high-reach Spanish-language podcasters in the consciousness/leadership space. Coordinate appearances timed to book pre-launch.

|  | Market Value | Contribution Rate (10%) |
| --- | --- | --- |
| Total | $8,000 | $800 |

_______________________________________________

# 4. Measurement & Monitoring Framework

Set up AI mention monitoring (EN + ES), citation tracking, inbound inquiry quality tracking, Substack analytics, community voice volume measurement, and enrollment source analysis.

|  | Market Value | Contribution Rate (10%) |
| --- | --- | --- |
| Total | $6,500 | $650 |

_______________________________________________

# 5. Cost Summary

## By Category

| Category | Market Value | Contribution Rate |
| --- | --- | --- |
| Pre-Launch Initiatives (1.1-1.8) | $92,500 | $9,250 |
| Conversion Bridge (2) | $14,000 | $1,400 |
| Strategic Partnerships (3.1-3.3) | $33,000 | $3,300 |
| Measurement Framework (4) | $6,500 | $650 |

## Grand Total -- Communication Architecture Implementation

|  | Market Value | Contribution Rate | Savings |
| --- | --- | --- | --- |
| Total | $146,000 | $14,600 | $131,400 (90%) |

$131,400 in value contributed directly to the mission -- in the same spirit of conscious contribution that ROSES OS extends to its community.

_______________________________________________

# 6. Overlap with Existing Scope of Work

The following items overlap with projects already defined in the Scope of Work & Economic Proposal:

| This Document | Scope of Work Equivalent | Overlap |
| --- | --- | --- |
| Schema Markup ($12,000) | GEO / Content Architecture ($12,000) | Full overlap |
| Conversion Bridge ($14,000) | Platform UX Refinement ($15,000) | Partial overlap |

Adjusted total (removing full overlaps): $134,000 market / $13,400 contribution

### Combined Project Totals (De-Duplicated)

| Scope | Market Value | Contribution Rate |
| --- | --- | --- |
| Scope of Work -- Phases 1 & 2 | $205,000 | $20,500 |
| Communication Architecture (de-duplicated) | $134,000 | $13,400 |
| Combined Total | $339,000 | $33,900 |

_______________________________________________

# 7. Prioritization Recommendation

Based on the Communication Architecture's emphasis on the 5-8 month pre-launch window:

### Immediate (Months 1-2)

Substack Migration -- $4,500 / $450

Schema Markup & Technical Infrastructure -- $12,000 / $1,200

First 4 GEO Blog Essays -- ~$8,000 / $800

### Near-Term (Months 2-4)

Spanish YouTube Channel Launch -- $22,000 / $2,200

Podcast Outreach & First Appearances -- $9,000 / $900

Community Voice Program Launch -- $6,000 / $600

### Pre-Launch (Months 4-8)

Remaining GEO Blog Essays -- ~$10,000 / $1,000

English YouTube Channel -- $16,000 / $1,600

Conversion Bridge Design -- $14,000 / $1,400

Strategic Partnerships Engaged -- $33,000 / $3,300

### Ongoing

Measurement Framework -- $6,500 / $650

Wikipedia Groundwork -- $5,000 / $500

_______________________________________________

# 8. Notes

All pricing follows the same milestone-based, outcome-driven structure as the Scope of Work -- payment tied to deliverable completion and acceptance, not hours worked.

The 90% contribution rate reflects the same mission-aligned pricing model, with the difference settleable through equity, program enrollment, and/or Numa land allocation.

The Communication Architecture PDF does not assign ownership to specific workstreams. Several initiatives (podcast appearances, community voice, founder visibility) require founder-led participation that cannot be outsourced.

Partnership costs (Section 3) are estimates for initial engagement. Ongoing partnership terms would be negotiated separately.

This is a starting point for conversation. All scope, pricing, and terms are open for discussion.

_______________________________________________

ROSES OS

Communication Architecture Cost Summary

March 2026 -- Version 1.0